## Backlog
Area | Feature/Interaction | Priority | Difficulty
|  | 1 = very important | 1 = easy | On the Schedule
|  | 2 = normal | 2 = medium
|  | 3 = less important | 3 = hard
Player Movement
| When the player dies, he cries, shrinks, and pops out of existence | 3 | 3
| The character smiles when he completes a layer | 2 | 1
Enemy Movement
| The Yellow Rectangle gets angry when the player is close | 3 | 1
| Flying Pink moves its' eyes when it pauses | 2 | 3
| The big Red enemy's bubble grows and shrinks while its' sleeping | 3 | 1
| The Yellow Rectangle Enemy sometimes falls down | 2 | 3
| Enemies Spawn in waves rather than individually | 2 | 3
Gameplay UI
| The player's best score is shown on the Gameplay screen | 2 | 1
| The Volume can be changed from the pause menu | 2 | 2
| A menu pops up when the player dies, allowing them to restart, return to menu, or quit | 1 | 2
Environment
| The Earth has more than just grass on it | 2 | 3
Sound
| Background music speeds up with the layers | 3 | 3
| Sound effect volume can be adjusted | 1 | 3
Menu
| Enemies appear on the main menu occasionally | 3 | 2
| The Player has different hats that he can change on the main menu | 3 | 3
| Volume settings from the last time played are the same after coming back | 2 | 2

## Week 2
Availability
|  |  | Person 1 | Person 2
|  | M | 6 | 0
|  | T | 0 | 0
|  | W | 6 | 0
NOTE: Week 1 was deleted |  | Th | 6 | 0
|  | F | 6 | 0
|  | Sa | 6 | 0
|  | Su | 0 | 0
|  | TOTAL | 30 | 0
| Student 1 Tasks |  |  |  | Student 1 Tasks (continued)
| Feature/Interaction | Priority | Difficulty | Estimate (hours) | Feature/Interaction | Priority | Difficulty | Estimate (hours) | Removed
| The Main Menu has Settings Button that lets you change the game volume | 1 | 1 | 2 |  |  |  |  | Working on
| The Big Red Enemy runs at you from the left or right of road | 1 | 2 | 2 |  |  |  |  | Completed
| They Flying Pink enemy randomly moves between six locations | 1 | 3 | 4
| The player animates when moving left/right | 2 | 1 | 1
| The character squinches his eyes when he is shrinking | 2 | 2 | 2
| The character changes color when he gets hurt, and dies when he loses all his color | 2 | 1 | 1
| Shrinking ability is limited by a resource on a bar | 2 | 2 | 4
| The controls are visible on the menu | 2 | 1 | 1
| The Player's best score is saved and viewable on the Main menu | 2 | 3 | 4
| The Character blinks occasionally | 3 | 1 | 2
| TOTAL |  |  | 23 | TOTAL |  |  | 0

## Week 3
Availability
|  | Person 1 | Person 2
| M | 6 | 0
| T | 6 | 0
| W | 6 | 0
| Th | 6 | 0
| F | 6 | 0
| Sa | 6 | 0
| Su | 0 | 0
| TOTAL | 36 | 0
Student 1 Tasks |  |  |  | Student 1 Tasks (continued)
Feature/Interaction | Priority | Difficulty | Estimate (hours) | Feature/Interaction | Priority | Difficulty | Estimate (hours) | Removed
Working on
Sound effect volume can be adjusted | 1 | 3 | 2 |  |  |  |  | Completed
A menu pops up when the player dies, allowing them to restart, return to menu, or quit | 1 | 2 | 2
The Volume can be changed from the pause menu | 2 | 2 | 2
The player's best score is shown on the Gameplay screen | 2 | 1 | 1
The character smiles when he completes a layer | 2 | 1 | 2
Flying Pink moves its' eyes when it pauses | 2 | 3 | 2
The big Red enemy's bubble grows and shrinks while its' sleeping | 3 | 1 | 1
Volume settings from the last time played are the same after coming back | 3 | 2 | 2
TOTAL |  |  | 14 | TOTAL |  |  | 0

## Week 4
Availability
|  | Person 1 | Person 2
| M | 0 | 0
| T | 0 | 0
| W | 0 | 0
| Th | 0 | 0
| F | 0 | 0
| Sa | 0 | 0
| Su | 0 | 0
| TOTAL | 0 | 0
Student 1 Tasks |  |  |  | Student 1 Tasks (continued)
Feature/Interaction | Priority | Difficulty | Estimate (hours) | Feature/Interaction | Priority | Difficulty | Estimate (hours) | Removed
Working on
Completed
TOTAL |  |  | 0 | TOTAL |  |  | 0

## CRCCards
Planet
|  | GameManager |  | Spin Self
|  | Track Score |  | Adjust Speed
|  | Track Layer |  | Change Texture
|  | Report UI updates |  | Change Background
Update SpawnManager
Update Planet
Menu |  | SoundControl |  | SpawnManager
Start Game |  | Player |  | Spawn random enemy
Change Volume | SceneDataTransfer | Planet |  | Select spawn location
Show Highest Score |  | UIManager |  | Game Manager
Show Highest Layer |  | SceneDataTransfer |  | Enemy
SoundControl |  | SpawnManager
SceneDataTransfer | UIManager
| Update Score UI |  | SoundControl
| Update Layer UI |  | Control Background Music
| Modify Shrink Bar |  | Control Sound Effects
Toggle Pause Menu
|  | Player |  | Enemy | Cave(Enemy Subclass)
|  | Receive left/right input |  | Idle animation | SpawnManager
|  | Receive down input |  | Aggro detection trigger
|  | Report enemy avoidance |  | Destroy self when leaving aggro | OtherEnemySubclasses
|  | Report narrow avoidance |  | Cause player death on collision
|  | Report death |  | Player
UI Manager
Game Manager
JiggleAnimation

## RefactoringNotes
Refactoring Notes
Good idea but difficult
Good idea but unsure of difficulty
Idea, but not sure if good yet
| Confirmed must do |  |  |  |  | Backup in a zip before you start | Check articles saved in favorites for reference | Refactoring Examples" in reference file for examples
|  | Category | Idea |  |  |  | Refactoring Tasks
|  | UI | Make dodge popup created by script rather than put in inspector | Graphics | Combine the Earth's surfaces so that it looks smoother | Resolve Layer transition problem | Broadcast player death and respond to it using receivers in the associated scripts. | Make the blink animation a separate script. Use interrupting co-routines method for it.
|  | Code | Make Big Red charge rotation based instead of transform based |  |  |  | Separate the score and layer feature from Game Manager | In Player animation, if a value becomes negative set it to 0
|  | Code | apply ternaries |  |  |  | Implement Quit menu and separate ''Quit Game' from main menu and game manager to become its' own class | Separate Eye control to external script.
|  | UI | Add mouse and icons to build settings |  |  |  | Make individual axes in the repeated scaling animation toggleable on/off. | Separate shrink power as a scriptable event
|  | UI | Make Dodge popup words variables and modfiable |  |  |  | For player Movement, get axis in update but perform the movement in fixed update. | Remove need for short pause before the player starts the game
|  | UI | Replace Fonts |  |  |  | Boradcast Changes in music and SFX volume and add listeners to enemies and the player to adjust their volumes accordingly | Spawn Manager Restoration Act

## AssetInventory
NOTE: Remember to Backup to main Document!
Filename | Description/Notes | URL of Original (if Applicable) | Red | Not Started
|  |  | Orange | In Progress
UI and Menus |  |  | Blue | Completed
>>Menus
AssetPhotoOp.png | Image to use as background for title screen, take a better screenshot when the menu is made
box_option1.png | Box to hold the start button | https://assetstore.unity.com/packages/2d/gui/icons/simple-ui-icons-147101#description
box_select1.png | Start Button | https://assetstore.unity.com/packages/2d/gui/icons/simple-ui-icons-147101#description
box_coin1.png | Pause Menu | https://assetstore.unity.com/packages/2d/gui/icons/simple-ui-icons-147101#description
icon_07.png | Settings Button | https://assetstore.unity.com/packages/2d/gui/icons/simple-ui-icons-147101#description
button_exit.png | Settings close button | https://assetstore.unity.com/packages/2d/gui/icons/simple-ui-icons-147101#description
>>>Menu Music and SFX
DM-CGS-15.wav | Menu Button Presses sfx | https://assetstore.unity.com/packages/audio/sound-fx/free-casual-game-sfx-pack-54116
4. Run and Run_loop.wav | Menu Background Music | https://assetstore.unity.com/packages/audio/music/pop/casual-action-run-jump-89648
Gameplay
>>>Environment
Earth.prefab | The Game Level, needs decoration on the grass
"Decoration" | Decoration for earth, low priority
Grass.png | Earth Texture | https://assetstore.unity.com/packages/2d/textures-materials/floors/five-seamless-tileable-ground-textures-57060
CrackedStoneA.png | Earth Texture | https://assetstore.unity.com/packages/2d/textures-materials/floors/cartoon-ground-and-floor-textures-68398
CrackedStoneB.png | Earth Texture | https://assetstore.unity.com/packages/2d/textures-materials/floors/cartoon-ground-and-floor-textures-68398
DirtGround.png | Cave Texture | https://assetstore.unity.com/packages/2d/textures-materials/floors/cartoon-ground-and-floor-textures-68398
FS000_Day_01 | Skybox | https://assetstore.unity.com/packages/2d/textures-materials/sky/fantasy-skybox-free-18353
1. Funky Road_loop.wav | Gameplay Background Music | https://assetstore.unity.com/packages/audio/music/pop/casual-action-run-jump-89648
Cave.Prefab | Cave for layer transitions
>>>UI
box_login3.png | Score Container | https://assetstore.unity.com/packages/2d/gui/icons/simple-ui-icons-147101#description
bar_exp.png | Shrink Bar | https://assetstore.unity.com/packages/2d/gui/icons/simple-ui-icons-147101#description
>>>Character Models
PlayerCube.prefab | Player
EvilRectangle.prefab | Obstacle 1
EvilFlyingPink.prefab | Obstacle 2
EvilBigGuy.prefab | Obstacle 3
>>>SFX
DM-CGS-06.wav | Layer completion SFX | https://assetstore.unity.com/packages/audio/sound-fx/free-casual-game-sfx-pack-54116
monster_mini_cutie_attack_long_6.wav | Passing Enemy SFX | https://assetstore.unity.com/packages/audio/sound-fx/creatures/mini-monsters-ultimate-voice-pack-53373
monster_mini_cutie_attack_fast_5.wav | Passing Enemy SFX | https://assetstore.unity.com/packages/audio/sound-fx/creatures/mini-monsters-ultimate-voice-pack-53373
monster_mini_cutie_attack_long_1.wav | Passing Enemy SFX | https://assetstore.unity.com/packages/audio/sound-fx/creatures/mini-monsters-ultimate-voice-pack-53373
monster_mini_cutie_damage_4.wav | Player health loss SFX | https://assetstore.unity.com/packages/audio/sound-fx/creatures/mini-monsters-ultimate-voice-pack-53373
monster_mini_cutie_damage_5.wav | Player health loss SFX | https://assetstore.unity.com/packages/audio/sound-fx/creatures/mini-monsters-ultimate-voice-pack-53373
monster_mini_cutie_damage_9.wav | Player health loss SFX | https://assetstore.unity.com/packages/audio/sound-fx/creatures/mini-monsters-ultimate-voice-pack-53373
monster_stupid_slick_attack_long_4.wav | Obstacle 1 impact SFX | https://assetstore.unity.com/packages/audio/sound-fx/creatures/mini-monsters-ultimate-voice-pack-53373
monster_spooky_pink_attack_fast_3.wav | Obstacle 2 impact SFX | https://assetstore.unity.com/packages/audio/sound-fx/creatures/mini-monsters-ultimate-voice-pack-53373
monster_potbellied_attack_fast_8.wav | Obstacle 3 impact SFX | https://assetstore.unity.com/packages/audio/sound-fx/creatures/mini-monsters-ultimate-voice-pack-53373
>>>Particles
SmokeyExplosion.prefab | Player death particle | https://assetstore.unity.com/packages/vfx/particles/sherbb-s-particle-collection-170798