## Backlog
Area | Feature/Interaction | Priority | Difficulty
|  | 1 = very important | 1 = easy | On the Schedule
|  | 2 = normal | 2 = medium
|  | 3 = less important | 3 = hard
Player Movement
Enemy Movement
Gameplay UI
Environment
Sound
Menu
| Enemies appear on the main menu occasionally | 3 | 2
| Facts about Coren appear on the menu occasionally | 3 | 3
| There is a credits section on the main menu that thanks the different asset providers from the Unity Store | 3 | 3
Distribution
Add ability to regain lives after layers

## Week 2
Availability
|  |  | Person 1 | Person 2
|  | M | 6 | 0
|  | T | 0 | 0
|  | W | 6 | 0
NOTE: Week 1 was deleted |  | Th | 6 | 0
|  | F | 6 | 0
|  | Sa | 6 | 0
|  | Su | 0 | 0
|  | TOTAL | 30 | 0
| Student 1 Tasks |  |  |  | Student 1 Tasks (continued)
| Feature/Interaction | Priority | Difficulty | Estimate (hours) | Feature/Interaction | Priority | Difficulty | Estimate (hours) | Removed
| The Main Menu has Settings Button that lets you change the game volume | 1 | 1 | 2 |  |  |  |  | Working on
| The Big Red Enemy runs at you from the left or right of road | 1 | 2 | 2 |  |  |  |  | Completed
| They Flying Pink enemy randomly moves between six locations | 1 | 3 | 4
| The player animates when moving left/right | 2 | 1 | 1
| The character squinches his eyes when he is shrinking | 2 | 2 | 2
| The character changes color when he gets hurt, and dies when he loses all his color | 2 | 1 | 1
| Shrinking ability is limited by a resource on a bar | 2 | 2 | 4
| The controls are visible on the menu | 2 | 1 | 1
| The Player's best score is saved and viewable on the Main menu | 2 | 3 | 4
| The Character blinks occasionally | 3 | 1 | 2
| TOTAL |  |  | 23 | TOTAL |  |  | 0

## Week 3
Availability
|  | Person 1 | Person 2
| M | 6 | 0
| T | 6 | 0
| W | 6 | 0
| Th | 6 | 0
| F | 6 | 0
| Sa | 6 | 0
| Su | 0 | 0
| TOTAL | 36 | 0
Student 1 Tasks |  |  |  | Student 1 Tasks (continued)
Feature/Interaction | Priority | Difficulty | Estimate (hours) | Feature/Interaction | Priority | Difficulty | Estimate (hours) | Removed
Working on
Sound effect volume can be adjusted | 1 | 3 | 2 |  |  |  |  | Completed
A menu pops up when the player dies, allowing them to restart, return to menu, or quit | 1 | 2 | 2
The Volume can be changed from the pause menu | 2 | 2 | 2
The player's best score is shown on the Gameplay screen | 2 | 1 | 1
The character smiles when he completes a layer | 2 | 1 | 2
Flying Pink moves its' eyes when it pauses | 2 | 3 | 2
The big Red enemy's bubble grows and shrinks while its' sleeping | 3 | 1 | 1
Volume settings from the last time played are the same after coming back | 3 | 2 | 2
TOTAL |  |  | 14 | TOTAL |  |  | 0

## Week 4
Availability
|  | Person 1 | Person 2
| M | 0 | 0
| T | 0 | 0
| W | 6 | 0
| Th | 6 | 0
| F | 6 | 0
| Sa | 6 | 0
| Su | 0 | 0
| TOTAL | 24 | 0
Student 1 Tasks |  |  |  | Student 1 Tasks (continued)
Feature/Interaction | Priority | Difficulty | Estimate (hours) | Feature/Interaction | Priority | Difficulty | Estimate (hours) | Removed
Working on
There's a large pink enemy that blocks the player with its' eyes | 2 | 2 | 2 |  |  |  |  | Completed
There are small rectangle enemies that spawn in groups | 2 | 2 | 4
The Yellow Rectangle can fall in the other direction | 1 | 2 | 1
Enemies gloat after they kill the player | 2 | 2 | 2
There's a popup when the Layer Transitions instead of a cave | 1 | 2 | 1
The Earth has more than just grass on it | 2 | 3 | 4
There is a loading screen between the menu and the game | 2 | 2 | 4
TOTAL |  |  | 18 | TOTAL |  |  | 0

## Week 5
Availability
|  | Person 1 | Person 2
| M | 0 | 0
| T | 0 | 0
| W | 0 | 0
| Th | 0 | 0
| F | 0 | 0
| Sa | 0 | 0
| Su | 0 | 0
| TOTAL | 0 | 0
Student 1 Tasks |  |  |  | Student 1 Tasks (continued)
Feature/Interaction | Priority | Difficulty | Estimate (hours) | Feature/Interaction | Priority | Difficulty | Estimate (hours) | Removed
Working on
Completed
TOTAL |  |  | 0 | TOTAL |  |  | 0

## CRCCards
Planet
|  | GameManager |  | Spin Self
|  | Track Score |  | Adjust Speed
|  | Track Layer |  | Change Texture
|  | Report UI updates |  | Change Background
Update SpawnManager
Update Planet
Menu |  |  |  | SpawnManager
Start Game |  |  |  | Spawn random enemy
Change Volume | SceneDataTransfer |  |  | Select spawn location
Show Highest Score
Show Highest Layer
UIManager
| Update Score UI | Player | SoundControl
| Update Layer UI | Receive left/right input | Control Background Music
| Modify Shrink Bar | Receive down input | Control Sound Effects
| Toggle Pause Menu | Report enemy avoidance
Report narrow avoidance
|  | Report death |  | Enemy | Cave(Enemy Subclass)
|  |  |  | Idle animation | SpawnManager
Aggro detection trigger
|  |  |  | Destroy self when leaving aggro | OtherEnemySubclasses
Cause player death on collision

## RefactoringNotes
Refactoring Notes
Good idea but difficult
Good idea but unsure of difficulty
Idea, but not sure if good yet
Confirmed must do
|  | Category | Idea
|  | UI | Add mouse and icons to build settings
|  | UI | Make Dodge popup words variables and modfiable
|  | Graphics | Combine the Earth's surfaces so that it looks smoother

## AssetInventory
NOTE: Remember to Backup to main Document!
Filename | Description/Notes | URL of Original (if Applicable) | Red | Not Started
|  |  | Orange | In Progress
UI and Menus |  |  | Blue | Completed
>>Menus
box_option1.png | Box to hold the start button | https://assetstore.unity.com/packages/2d/gui/icons/simple-ui-icons-147101#description
box_select1.png | Start Button | https://assetstore.unity.com/packages/2d/gui/icons/simple-ui-icons-147101#description
box_coin1.png | Pause Menu | https://assetstore.unity.com/packages/2d/gui/icons/simple-ui-icons-147101#description
icon_07.png | Settings Button | https://assetstore.unity.com/packages/2d/gui/icons/simple-ui-icons-147101#description
button_exit.png | Settings close button | https://assetstore.unity.com/packages/2d/gui/icons/simple-ui-icons-147101#description
box_login3.png | Score Container | https://assetstore.unity.com/packages/2d/gui/icons/simple-ui-icons-147101#description
bar_exp.png | Shrink Bar | https://assetstore.unity.com/packages/2d/gui/icons/simple-ui-icons-147101#description
JazzCreateBubble.ttf | Custom Font | https://assetstore.unity.com/packages/2d/fonts/bubble-font-free-version-24987#description
>>>Menu Music and SFX
DM-CGS-1.wav | Menu Button Presses sfx | https://assetstore.unity.com/packages/audio/sound-fx/free-casual-game-sfx-pack-54116
4. Run and Run_loop.wav | Menu Background Music | https://assetstore.unity.com/packages/audio/music/pop/casual-action-run-jump-89648
Gameplay
>>>Environment
Grass.png | Earth Texture | https://assetstore.unity.com/packages/2d/textures-materials/floors/five-seamless-tileable-ground-textures-57060
CrackedStoneA.png | Earth Texture | https://assetstore.unity.com/packages/2d/textures-materials/floors/cartoon-ground-and-floor-textures-68398
CrackedStoneB.png | Earth Texture | https://assetstore.unity.com/packages/2d/textures-materials/floors/cartoon-ground-and-floor-textures-68398
DirtGround.png | Cave Texture | https://assetstore.unity.com/packages/2d/textures-materials/floors/cartoon-ground-and-floor-textures-68398
ForestFloorGreen.png | Tree Texture | https://assetstore.unity.com/packages/2d/textures-materials/floors/cartoon-ground-and-floor-textures-68398
SmoothSand.png | Tree Texture | https://assetstore.unity.com/packages/2d/textures-materials/floors/cartoon-ground-and-floor-textures-68398
FS000_Day_01 | Skybox | https://assetstore.unity.com/packages/2d/textures-materials/sky/fantasy-skybox-free-18353
1. Funky Road_loop.wav | Gameplay Background Music | https://assetstore.unity.com/packages/audio/music/pop/casual-action-run-jump-89648
>>>Character Models
PlayerCube.prefab | Player
EvilRectangle.prefab | Obstacle 1
EvilFlyingPink.prefab | Obstacle 2
EvilBigGuy.prefab | Obstacle 3
EvilFlyingBlack.prefab | Obstacle 4
EvilRectangleOrangeMini.prefab | Obstacle 5
>>>SFX
monster_mini_cutie_attack_long_8.wav | Layer completion SFX | https://assetstore.unity.com/packages/audio/sound-fx/creatures/mini-monsters-ultimate-voice-pack-53373
monster_mini_cutie_battle_4.wav | Layer completion SFX | https://assetstore.unity.com/packages/audio/sound-fx/creatures/mini-monsters-ultimate-voice-pack-53373
monster_mini_cutie_battle_6.wav | Layer completion SFX | https://assetstore.unity.com/packages/audio/sound-fx/creatures/mini-monsters-ultimate-voice-pack-53373
monster_mini_cutie_attack_long_6.wav | Passing Enemy SFX | https://assetstore.unity.com/packages/audio/sound-fx/creatures/mini-monsters-ultimate-voice-pack-53373
monster_mini_cutie_attack_fast_5.wav | Passing Enemy SFX | https://assetstore.unity.com/packages/audio/sound-fx/creatures/mini-monsters-ultimate-voice-pack-53373
monster_mini_cutie_attack_long_1.wav | Passing Enemy SFX | https://assetstore.unity.com/packages/audio/sound-fx/creatures/mini-monsters-ultimate-voice-pack-53373
monster_mini_cutie_dead_6.wav | Player Death SFX | https://assetstore.unity.com/packages/audio/sound-fx/creatures/mini-monsters-ultimate-voice-pack-53373
monster_mini_cutie_dead_7.wav | Player Death SFX | https://assetstore.unity.com/packages/audio/sound-fx/creatures/mini-monsters-ultimate-voice-pack-53373
monster_mini_cutie_dead_8.wav | Player Death SFX | https://assetstore.unity.com/packages/audio/sound-fx/creatures/mini-monsters-ultimate-voice-pack-53373
monster_mini_cutie_damage_4.wav | Player health loss SFX | https://assetstore.unity.com/packages/audio/sound-fx/creatures/mini-monsters-ultimate-voice-pack-53373
monster_mini_cutie_damage_5.wav | Player health loss SFX | https://assetstore.unity.com/packages/audio/sound-fx/creatures/mini-monsters-ultimate-voice-pack-53373
monster_mini_cutie_damage_9.wav | Player health loss SFX | https://assetstore.unity.com/packages/audio/sound-fx/creatures/mini-monsters-ultimate-voice-pack-53373
>>>Particles
BigSmoke.prefab | Player death particle | https://assetstore.unity.com/packages/vfx/particles/sherbb-s-particle-collection-170798