## Steps
Weekly Planning Process
1. Update your backlog.
Are there things in it that you decided not to build at all, or which proved to be redundant? Delete them. Did you identify new work during the past week? Add stories. Has the priority of any feature changed in light of the week's progress? Update the priority.
2. Choose items from the backlog for the current iteration.
Look at your backlog. Pick items from it that you think would make sense for this iteration. Which features have the greatest impact on the game experience? Try to choose at least one task that will let you see visible progress.
3. Make rough lists of tasks for each team member.
Decide who will do each of the priority 1 items. Turn the items into detailed tasks (the individual steps that would be needed to implement the feature).
4. Assign detailed time estimates to the tasks.
Given the skills of the team member who would be doing it, how many hours would it take to complete each task? If the answer is more than eight hours, break the task down further.
5. Estimate your actual availability.
Look at each day of the week (Monday - Sunday) and think about your existing commitments. (Round up, not down.) Out of the free time you have that day (if any), estimate how many hours you could devote to this project.
6. Make sure your tasks line up with your availability.
Add up the total hours for the tasks you've chosen and your total availability for the week. If your tasks are greater than your availability by 10% or more, make a choice: either cut your other commitments, or cut down your list of tasks.

## Example Backlog
The backlog is where you'll keep your overall "to-do" list for the project. When you add something, give it a priority representing how important it is right now (the moment you add it). Then give it a rough estimate of difficulty.
Area | Feature/Interaction | Priority | Difficulty
|  | 1 = very important | 1 = easy
|  | 2 = normal | 2 = medium
|  | 3 = less important | 3 = hard
Player
| Player input makes ship move | 1 | 3
| Player can fire bullets | 1 | 3
| Only two bullets on screen | 2 | 3
Enemies
| Enemies have sprites | 1 | 1
| Enemies disappear when bullets hit them | 1 | 1
| Enemies fire bullets | 2 | 2
| Enemies dive-bomb | 2 | 1
| Enemies fly in | 2 | 1
Score
| Shooting an enemy changes current score | 2 | 2
| Shooting an enemy shows score floater on screen | 2 | 3
| Score for enemy reflects game state | 3 | 3
| Show high score on screen | 3 | 1
GUI
| Level indicator shown on screen | 3 | 1
| Score is visible on screen | 1 | 2

## Example Week
Availability
|  | Person 1 | Person 2
| M | 3 | 3
| T | 2 | 2
| W | 0 | 4
| Th | 0 | 0
| F | 0 | 0
| Sa | 2 | 2
| Su | 3 | 5
| TOTAL | 10 | 16
Student 1 Tasks |  |  |  | Student 2 Tasks
Feature/Interaction | Priority | Difficulty | Estimate (hours) | Feature/Interaction | Priority | Difficulty | Estimate (hours)
Player input makes ship move | 1 | 1 |  | Enemies have sprites | 1 | 1
Listen for arrow keys in Update |  |  | 0.5 | import sprite sheet and cut sprites |  |  | 1
Make left/right rotate ship |  |  | 1 | attach sprites to enemy prefabs by type |  |  | 2
Make up accelerate ship |  |  | 1
Limit maximum velocity |  |  | 1
|  |  |  | Enemies disappear when bullets hit them | 1 | 3
|  |  |  | set up colliders, rigidbodies, etc. |  |  | 3
Player can fire bullets | 1 | 3 |  | detect collision with bullet (show console message) |  |  | 1
Make bullet prefab |  |  | 1 | on collision with bullet, start death animation and play sound |  |  | 1
Bullet moves in a straight path forwards from player, i.e. following player's rotation |  |  | 1 | figure out how to swap sprites with delay to create blinking effect |  |  | 4
Instantiate bullet at spawn point |  |  | 2 | destroy enemy gameObject after death animation |  |  | 2
Listen for space key in Update |  |  | 0.5
TOTAL |  |  | 8 | TOTAL |  |  | 14

## Backlog
Area | Feature/Interaction | Priority | Difficulty
|  | 1 = very important | 1 = easy | On the Schedule
|  | 2 = normal | 2 = medium
|  | 3 = less important | 3 = hard
Player Movement
| The player dies in a dramatic fashion | 3 | 3
| The character seems happy when he completes a layer | 3 | 1
| The Character blinks occasionally | 3 | 1
| The character squinches his eyes when he is shrinking | 2 | 2
| The character changes color when he gets hurt, and dies when he loses all his color | 2 | 1
| Visual indicator for Iframes | 3 | 3
Enemy Movement
| The Yellow Rectangle gets angry when the player is close | 3 | 1
| They Flying Pink enemy randomly moves between six locations | 1 | 3
| The Yellow Rectangle Enemy sometimes falls down | 3 | 3
Gameplay UI
| The player's best score is shown on the Gameplay screen | 3 | 3
| Shrinking ability is limited by a resource on a bar | 2 | 2
Environment
| The planet and sky change appearance when the layer transitions | 3 | 3
Sound
| Background music speeds up with the layers | 3 | 3
| Add control over SFX to sound control | 3 | 3
Menu
| The controls aare visible on the menu | 2 | 2
| Enemies appear on the main menu occasionally | 3 | 2
| The Volume can be changed from the pause menu | 3 | 2
| The Player's best score is saved and viewable on the Main menu | 2 | 3

## Week 2
Availability
|  |  | Person 1 | Person 2
|  | M | 6 | 0
|  | T | 0 | 0
|  | W | 6 | 0
NOTE: Week 1 was deleted |  | Th | 6 | 0
|  | F | 6 | 0
|  | Sa | 6 | 0
|  | Su | 0 | 0
|  | TOTAL | 30 | 0
| Student 1 Tasks |  |  |  | Student 1 Tasks (continued)
| Feature/Interaction | Priority | Difficulty | Estimate (hours) | Feature/Interaction | Priority | Difficulty | Estimate (hours) | Removed
| The Main Menu has Settings Button that lets you change the game volume | 1 | 1 | 2 |  |  |  |  | Working on
| The Big Red Enemy runs at you from the left or right of road | 1 | 2 | 2 |  |  |  |  | Completed
| They Flying Pink enemy randomly moves between six locations | 1 | 3 | 4
| The player animates when moving left/right | 2 | 1 | 1
| The character squinches his eyes when he is shrinking | 2 | 2 | 2
| The character changes color when he gets hurt, and dies when he loses all his color | 2 | 1 | 1
| Shrinking ability is limited by a resource on a bar | 2 | 2 | 4
| The controls are visible on the menu | 2 | 1 | 1
| The Player's best score is saved and viewable on the Main menu | 2 | 3 | 4
| The Character blinks occasionally | 3 | 1 | 2
| TOTAL |  |  | 23 | TOTAL |  |  | 0

## Week 3
Availability
|  | Person 1 | Person 2
| Th | 0 | 0
| F | 0 | 0
| Sa | 0 | 0
| Su | 0 | 0
| M | 0 | 0
| T | 0 | 0
| W | 0 | 0
| TOTAL | 0 | 0
Student 1 Tasks |  |  |  | Student 1 Tasks (continued)
Feature/Interaction | Priority | Difficulty | Estimate (hours) | Feature/Interaction | Priority | Difficulty | Estimate (hours) | Removed
Working on
Completed
TOTAL |  |  | 0 | TOTAL |  |  | 0

## CRCCards
|  | UIManager | Planet
|  | Update Score UI | Spin Self
|  | Update Layer UI | Adjust Speed
|  | Update Multiplier | Change Texture
|  | Toggle Pause Menu | Change Background
Menu |  | GameManager | SpawnManager
Start Game |  | Track Score | Spawn random enemy
Change Volume |  | Track Layer | Select spawn location
Show Highest Score | SceneDataTransfer | Report UI updates | Game Manager
Show Highest Layer |  | Update SpawnManager | Enemy
SoundControl |  | Update Planet
SceneDataTransfer |  | SoundControl
|  | Player | SoundControl
|  | Planet | Control Background Music
|  | UIManager | Control Sound Effects
SceneDataTransfer
SpawnManager
|  |  | Enemy | Cave(Enemy Subclass)
|  | Player | Idle animation | SpawnManager
|  | Receive left/right input | Aggro detection trigger
|  | Receive down input | Destroy self when leaving aggro | OtherEnemySubclasses
|  | Report enemy avoidance | Cause player death on collision
|  | Report narrow avoidance | Player
Report death
Game Manager
AnimationMaker

## RefactoringNotes
Refactoring Notes
Good idea but difficult
Good idea but unsure of difficulty
Idea, but not sure if good yet
Confirmed must do
|  | Category | Idea | Category | Idea | Category | Idea
|  | Sound | Give the Sound Control script authority over individual sound effects for greater volume control | Art | Earth Extensive Decoration | Art | Hat selection?!?
|  | Gameplay | Add some variance to spawn timing | UI | Replace Fonts | Code | The system remembers the volume you used and saves it
|  | Code | Remove scorekeeping responsibilities from GameManager into a new script | UI | Buttons highlight when the mouse is over them | Code | apply ternaries
|  | UI | Make dodge popup created by script rather than put in inspector | Graphics | Give character dust-kickup effect | Animation | Make the character change z-axis size when it strafe animates
|  | UI | Make Dodge popup words variables and modfiable | Graphics | Make it darker near the cave entrance
|  | Animation | Make the player animate when it dodges | UI | Add mouse and icons to build settings

## AssetInventory
NOTE: Remember to Backup to main Document!
Filename | Description/Notes | URL of Original (if Applicable) | Red | Not Started
|  |  | Orange | In Progress
UI and Menus |  |  | Blue | Completed
>>Menus
AssetPhotoOp.png | Image to use as background for title screen, take a better screenshot when the menu is made
box_option1.png | Box to hold the start button | https://assetstore.unity.com/packages/2d/gui/icons/simple-ui-icons-147101#description
box_select1.png | Start Button | https://assetstore.unity.com/packages/2d/gui/icons/simple-ui-icons-147101#description
box_coin1.png | Pause Menu | https://assetstore.unity.com/packages/2d/gui/icons/simple-ui-icons-147101#description
icon_07.png | Settings Button | https://assetstore.unity.com/packages/2d/gui/icons/simple-ui-icons-147101#description
button_exit.png | Settings close button | https://assetstore.unity.com/packages/2d/gui/icons/simple-ui-icons-147101#description
>>>Menu Music and SFX
DM-CGS-15.wav | Menu Button Presses sfx | https://assetstore.unity.com/packages/audio/sound-fx/free-casual-game-sfx-pack-54116
4. Run and Run_loop.wav | Menu Background Music | https://assetstore.unity.com/packages/audio/music/pop/casual-action-run-jump-89648
Gameplay
>>>Environment
Earth.prefab | The Game Level, needs decoration on the grass
"Decoration" | Decoration for earth, low priority
Grass.png | Earth Texture | https://assetstore.unity.com/packages/2d/textures-materials/floors/five-seamless-tileable-ground-textures-57060
CrackedStoneA.png | Earth Texture | https://assetstore.unity.com/packages/2d/textures-materials/floors/cartoon-ground-and-floor-textures-68398
CrackedStoneB.png | Earth Texture | https://assetstore.unity.com/packages/2d/textures-materials/floors/cartoon-ground-and-floor-textures-68398
DirtGround.png | Cave Texture | https://assetstore.unity.com/packages/2d/textures-materials/floors/cartoon-ground-and-floor-textures-68398
FS000_Day_01 | Skybox | https://assetstore.unity.com/packages/2d/textures-materials/sky/fantasy-skybox-free-18353
1. Funky Road_loop.wav | Gameplay Background Music | https://assetstore.unity.com/packages/audio/music/pop/casual-action-run-jump-89648
Cave.Prefab | Cave for layer transitions
>>>UI
box_login3.png | Score Container | https://assetstore.unity.com/packages/2d/gui/icons/simple-ui-icons-147101#description
>>>Character Models
PlayerCube.prefab | Player
EvilRectangle.prefab | Obstacle 1
EvilFlyingPink.prefab | Obstacle 2
EvilBigGuy.prefab | Obstacle 3
>>>SFX
DM-CGS-06.wav | Layer completion SFX | https://assetstore.unity.com/packages/audio/sound-fx/free-casual-game-sfx-pack-54116
monster_mini_cutie_attack_long_6.wav | Passing Enemy SFX | https://assetstore.unity.com/packages/audio/sound-fx/creatures/mini-monsters-ultimate-voice-pack-53373
monster_mini_cutie_attack_fast_5 | Passing Enemy SFX | https://assetstore.unity.com/packages/audio/sound-fx/creatures/mini-monsters-ultimate-voice-pack-53373
monster_mini_cutie_attack_long_1 | Passing Enemy SFX | https://assetstore.unity.com/packages/audio/sound-fx/creatures/mini-monsters-ultimate-voice-pack-53373
monster_stupid_slick_attack_long_4.wav | Obstacle 1 impact SFX | https://assetstore.unity.com/packages/audio/sound-fx/creatures/mini-monsters-ultimate-voice-pack-53373
monster_spooky_pink_attack_fast_3.wav | Obstacle 2 impact SFX | https://assetstore.unity.com/packages/audio/sound-fx/creatures/mini-monsters-ultimate-voice-pack-53373
monster_potbellied_attack_fast_8.wav | Obstacle 3 impact SFX | https://assetstore.unity.com/packages/audio/sound-fx/creatures/mini-monsters-ultimate-voice-pack-53373
>>>Particles
SmokeyExplosion.prefab | Player death particle | https://assetstore.unity.com/packages/vfx/particles/sherbb-s-particle-collection-170798