## Steps
Weekly Planning Process
1. Update your backlog.
Are there things in it that you decided not to build at all, or which proved to be redundant? Delete them. Did you identify new work during the past week? Add stories. Has the priority of any feature changed in light of the week's progress? Update the priority.
2. Choose items from the backlog for the current iteration.
Look at your backlog. Pick items from it that you think would make sense for this iteration. Which features have the greatest impact on the game experience? Try to choose at least one task that will let you see visible progress.
3. Make rough lists of tasks for each team member.
Decide who will do each of the priority 1 items. Turn the items into detailed tasks (the individual steps that would be needed to implement the feature).
4. Assign detailed time estimates to the tasks.
Given the skills of the team member who would be doing it, how many hours would it take to complete each task? If the answer is more than eight hours, break the task down further.
5. Estimate your actual availability.
Look at each day of the week (Monday - Sunday) and think about your existing commitments. (Round up, not down.) Out of the free time you have that day (if any), estimate how many hours you could devote to this project.
6. Make sure your tasks line up with your availability.
Add up the total hours for the tasks you've chosen and your total availability for the week. If your tasks are greater than your availability by 10% or more, make a choice: either cut your other commitments, or cut down your list of tasks.

## Example Backlog
The backlog is where you'll keep your overall "to-do" list for the project. When you add something, give it a priority representing how important it is right now (the moment you add it). Then give it a rough estimate of difficulty.
Area | Feature/Interaction | Priority | Difficulty
|  | 1 = very important | 1 = easy
|  | 2 = normal | 2 = medium
|  | 3 = less important | 3 = hard
Player
| Player input makes ship move | 1 | 3
| Player can fire bullets | 1 | 3
| Only two bullets on screen | 2 | 3
Enemies
| Enemies have sprites | 1 | 1
| Enemies disappear when bullets hit them | 1 | 1
| Enemies fire bullets | 2 | 2
| Enemies dive-bomb | 2 | 1
| Enemies fly in | 2 | 1
Score
| Shooting an enemy changes current score | 2 | 2
| Shooting an enemy shows score floater on screen | 2 | 3
| Score for enemy reflects game state | 3 | 3
| Show high score on screen | 3 | 1
GUI
| Level indicator shown on screen | 3 | 1
| Score is visible on screen | 1 | 2

## Example Week
Availability
|  | Person 1 | Person 2
| M | 3 | 3
| T | 2 | 2
| W | 0 | 4
| Th | 0 | 0
| F | 0 | 0
| Sa | 2 | 2
| Su | 3 | 5
| TOTAL | 10 | 16
Student 1 Tasks |  |  |  | Student 2 Tasks
Feature/Interaction | Priority | Difficulty | Estimate (hours) | Feature/Interaction | Priority | Difficulty | Estimate (hours)
Player input makes ship move | 1 | 1 |  | Enemies have sprites | 1 | 1
Listen for arrow keys in Update |  |  | 0.5 | import sprite sheet and cut sprites |  |  | 1
Make left/right rotate ship |  |  | 1 | attach sprites to enemy prefabs by type |  |  | 2
Make up accelerate ship |  |  | 1
Limit maximum velocity |  |  | 1
|  |  |  | Enemies disappear when bullets hit them | 1 | 3
|  |  |  | set up colliders, rigidbodies, etc. |  |  | 3
Player can fire bullets | 1 | 3 |  | detect collision with bullet (show console message) |  |  | 1
Make bullet prefab |  |  | 1 | on collision with bullet, start death animation and play sound |  |  | 1
Bullet moves in a straight path forwards from player, i.e. following player's rotation |  |  | 1 | figure out how to swap sprites with delay to create blinking effect |  |  | 4
Instantiate bullet at spawn point |  |  | 2 | destroy enemy gameObject after death animation |  |  | 2
Listen for space key in Update |  |  | 0.5
TOTAL |  |  | 8 | TOTAL |  |  | 14

## Backlog
Area | Feature/Interaction | Priority | Difficulty
|  | 1 = very important | 1 = easy
|  | 2 = normal | 2 = medium
|  | 3 = less important | 3 = hard
Player Movement
| The player can move left and right smoothly | 1 | 2 | On the Schedule
| The player can't leave the road | 1 | 3 | Completed
| The player animates while autorunning | 3 | 1
| Remake the character | 2 | 2
| The player animates when moving left/right | 2 | 2
| The player explodes when he dies | 3 | 1
| The player receives points when passing an enemy | 2 | 1
| The player can avoid enemies by a narrow margin for a score multiplier | 2 | 3
| The player is notified when an enemy is dodged narrowly | 2 | 2
| The character reacts when completing a layer | 3 | 2
| The character animates when shrinking | 3 | 2
| The player can press a button to shrink the character | 2 | 3
Enemy Movement
| Enemies animate in response to the players presence | 3 | 2
| Enemies kill the player on impact | 1 | 2
| Enemies spawn periodically on the road | 1 | 1
| EvilRectangles spawn locations are randomized | 2 | 2
| Implement Big Red | 2 | 2
| Implement Flying Pink | 2 | 2
| Add Player detection to enemies | 1 | 3
| Enemies animate when idle | 3 | 2
UI
| The layer and score are displayed to the player | 1 | 1
| The player's best score is shown on the screen | 3 | 3
| The player can choose to restart after they die | 2 | 3
Environment
| The planet rotates automatically | 1 | 1
| The planet and sky change appearance on layer transition | 3 | 2
| The Game changes layers at an interval | 2 | 2
| There is an environmental animation when the layer changes | 3 | 3
Sound
| Enemies makes sounds when the player passes them | 3 | 1
| The player character makes a sound when they die | 3 | 1
| Background music plays constantly | 2 | 1
| Sound effects can have their volume adjusted | 3 | 3
| Background music speeds up with the layers | 3 | 2
Menu
| There is a main Menu Screen | 2 | 3
| The Main Menu has Settings | 3 | 3
| The Main Menu has a background image | 3 | 2
| There is a Pause Menu | 2 | 3
Settings can be accessed from the pause menu

## Week 1
Availability
|  | Person 1 | Person 2
| M | 0 | 0
| T | 0 | 0
| W | 6 | 0
| Th | 6 | 0
| F | 6 | 0
| Sa | 0 | 0
| Su | 0 | 0
| TOTAL | 18 | 0
Student 1 Tasks |  |  |  | Student 1 Tasks (continued)
Feature/Interaction | Priority | Difficulty | Estimate (hours) | Feature/Interaction | Priority | Difficulty | Estimate (hours) | Removed
There is a main Menu Screen | 2 | 3 |  | The player animates when moving left/right | 2 | 2 |  | Working on
Turn the Main Game into a scene |  |  | 0.5 | Choose a particle affect to show when the player moves. Load into game, add to list, then make it a child of object the graphic is attached to (not the character!) |  |  | 1 | Completed
Make another scene for the menu |  |  | 0.5 | If the character moves left or right and the opposing horizontal axis is maxed, let it should trigger the particle in that direction. |  |  | 1
Add generic background, settings button, highscore placeholder, and Start/Quit game button |  |  | 0.5 | The particle size should be based on the character's current size, but not change if the char acter resizes afterwards. |  |  | 1
Ensure Start button can go to the game scene |  |  | 1 | The character should look in the direction their moving |  |  | 1
When the player dies, Let them return to the main menu or quit. |  |  | 1
Ensure Quit Button Works as intended |  |  | 1 | Implement Big Red | 2 | 2
|  |  |  | Bring Big Red(Teeth Mode) into the scene, give him his own child script. Set his offset so that he fits when facing the player on the left and right sides of the road |  |  | 0.5
There is a Pause Menu | 2 | 3 |  | Make him spawn on either the left or right side. |  |  | 0.5
In GameManager, pause the game time when 'Escape' is pressed. Ensure other elements are paused as well. |  |  | 1 | Make him run at the player directly |  |  | 1
Create a pause Screen that fades the background and shows 'paused' when the game is paused. This should be controlled by UI manager. |  |  | 1 | Make him run in zigzags, randomly chosen whether he does zig zags or runs straight |  |  | 1.5
Reduce music volume by 90% while the game is paused, returning to prior values afterward. |  |  | 0.5
The pause menu should have a button to return to main menu. |  |  | 0.5 | Implement Flying Pink | 2 | 2
|  |  |  | Bring Flying pink into the scene, with her own child script. Have her spawn in the center, offset above the ground above the player collider. |  |  | 0.5
|  |  |  | Have her move between 6 positions in a 2x3 grid. |  |  | 1
|  |  |  | Have her move her eyes in the direction she's moving |  |  | 1
|  |  |  | Have her eyes move in two separate directions, with one of the directions being the place she will move |  |  | 1
TOTAL |  |  | 7.5 | TOTAL |  |  | 11

## CRCCards
| UIManager | Planet
| Update Score UI | Spin Self
| Update Layer UI | Adjust Speed
| Update Multiplier | Change Texture
| Toggle Pause Menu | Change Background
Game Manager
Menu | GameManager | SpawnManager
Start Game | Track Score | Spawn random enemy
Change Volume | Track Layer | Select spawn location
Show Highest Score | Track Multipler | Game Manager
Show Highest Layer | Report UI updates | Enemy
Update SpawnManager
Update Planet
| SoundControl | SoundControl
| Player | Control Background Music
| Planet | Control Sound Effects
| UIManager | GameManager
| SpawnManager | SpawnManager
Enemy
| Player | Player
Receive left/right input
| Receive down input | Enemy
| Report enemy avoidance | Idle animation
| Report narrow avoidance | Aggro detection trigger
| Report death | Destroy self when leaving aggro
| Game Manager | Cause player death on collision
Player

## RefactoringNotes
Refactoring Notes
Good idea but difficult
Good idea but unsure of difficulty
Idea, but not sure if good yet
Confirmed must do
|  | Category | Idea | Category | Idea
|  | Sound | Give the Sound Control script authority over individual sound effects for greater volume control | UI | Dodge popups change appearance based on multiplier
|  | Art | Make the Player asset an actual slime | Gameplay | Add some variance to spawn timing
|  | Code | Remove scorekeeping responsibilities from GameManager into a new script | Animation | Eyes look in the direction of movement
|  | UI | Make dodge popup created by script rather than put in inspector | Sound | Add SFX to shrinking
|  | UI | Make Dodge popup words variables and modfiable | Gameplay | Add Big Red sleep mode
|  | Animation | Make the player animate when it dodges | Gameplay | Evil Rectangle should occasionally fall over
|  | Audio | Speed up sfx audio as game progresses

## AssetInventory
NOTE: Remember to Backup to main Document!
Filename | Description/Notes | URL of Original (if Applicable) | Red | Not Started
|  |  | Orange | In Progress
UI and Menus |  |  | Blue | Completed
>>Menus
AssetPhotoOp.png | Image to use as background for title screen, take a better screenshot when the menu is made
box_option1.png | Box to hold the start button | https://assetstore.unity.com/packages/2d/gui/icons/simple-ui-icons-147101#description
box_select1.png | Start Button | https://assetstore.unity.com/packages/2d/gui/icons/simple-ui-icons-147101#description
box_coin1.png | Pause Menu | https://assetstore.unity.com/packages/2d/gui/icons/simple-ui-icons-147101#description
>>>Menu Music and SFX
DM-CGS-15.wav | Menu Button Presses sfx | https://assetstore.unity.com/packages/audio/sound-fx/free-casual-game-sfx-pack-54116
4. Run and Run_loop.wav | Menu Background Music | https://assetstore.unity.com/packages/audio/music/pop/casual-action-run-jump-89648
Gameplay
>>>Environment
Earth.prefab | The Game Level, needs decoration on the grass
"Decoration" | Decoration for earth, low priority
Grass.png | Earth Texture | https://assetstore.unity.com/packages/2d/textures-materials/floors/five-seamless-tileable-ground-textures-57060
CrackedStoneA.png | Earth Texture | https://assetstore.unity.com/packages/2d/textures-materials/floors/cartoon-ground-and-floor-textures-68398
CrackedStoneB.png | Earth Texture | https://assetstore.unity.com/packages/2d/textures-materials/floors/cartoon-ground-and-floor-textures-68398
FS000_Day_01 | Skybox | https://assetstore.unity.com/packages/2d/textures-materials/sky/fantasy-skybox-free-18353
1. Funky Road_loop.wav | Gameplay Background Music | https://assetstore.unity.com/packages/audio/music/pop/casual-action-run-jump-89648
>>>UI
box_login3.png | Score Container | https://assetstore.unity.com/packages/2d/gui/icons/simple-ui-icons-147101#description
>>>Character Models
PlayerCube.prefab | Player
EvilRectangle.prefab | Obstacle 1
EvilFlyingPink.prefab | Obstacle 2
EvilBigGuy.prefab | Obstacle 3
>>>SFX
DM-CGS-06.wav | Layer completion SFX | https://assetstore.unity.com/packages/audio/sound-fx/free-casual-game-sfx-pack-54116
monster_mini_cutie_attack_long_6.wav | Passing Enemy SFX | https://assetstore.unity.com/packages/audio/sound-fx/creatures/mini-monsters-ultimate-voice-pack-53373
monster_mini_cutie_attack_fast_5 | Passing Enemy SFX | https://assetstore.unity.com/packages/audio/sound-fx/creatures/mini-monsters-ultimate-voice-pack-53373
monster_mini_cutie_attack_long_1 | Passing Enemy SFX | https://assetstore.unity.com/packages/audio/sound-fx/creatures/mini-monsters-ultimate-voice-pack-53373
monster_stupid_slick_attack_long_4.wav | Obstacle 1 impact SFX | https://assetstore.unity.com/packages/audio/sound-fx/creatures/mini-monsters-ultimate-voice-pack-53373
monster_spooky_pink_attack_fast_3.wav | Obstacle 2 impact SFX | https://assetstore.unity.com/packages/audio/sound-fx/creatures/mini-monsters-ultimate-voice-pack-53373
monster_potbellied_attack_fast_8.wav | Obstacle 3 impact SFX | https://assetstore.unity.com/packages/audio/sound-fx/creatures/mini-monsters-ultimate-voice-pack-53373
>>>Particles
SmokeyExplosion.prefab | Player death particle | https://assetstore.unity.com/packages/vfx/particles/sherbb-s-particle-collection-170798